# 6 Oct 2026 | FIT4701/2 Meeting - Agentic AI Platf…

6 Oct 2026 | FIT4701/2 Meeting - Agentic AI Platform

Attendees: ABM Russel Aryan Cyrus Ubaid Irfan

Notes

- Background - Intro + Lit survey + methodology draft is ready - AR will review.

- Get started with Ethics and run before or during FYP-B.  - Need a prototype ready (static role) - live link in the survey ..

  - Docs 80% Done, to be reviewed by Russel

- Access to overleaf - done

- Introduction - Background/Lit review - Methodology - Preliminary results - Future work in S2.ongoing

- RRQs. Added to the daft pending AR review

- Methodology - Calculation ??? source (why this eq should remain same in our project) - ongoing

- Preliminary results - Personas - done, FR & NFRs - done, Mockups - done, survey design - todo, data matched with RQs - ongoing, identified all constraints - ongoing, benchmarks (own + literature) -onging - backed by stats…

- Week 9 - Introduction + Background/Lit review (including RQs) + WORK ON PROTOTYPE FIRST DRAFT DONE - AR to review

- Week 10 - Methodology + Preliminary result

- Week 11- Final draft

- Week 12 - Submit

- Make Ai agents dynamic - Static [need to control the outcome + constraints/guardrails]: ongoing - review by expert human (periodically updated responses for same participants)

- Need a working prototype for Ethics (req gathering + evaluation) FIRST DRAFT DONE

- Create a workflow diagram - user journey flow chart. Part of the methodology section.

- Prototype is separate from survey questions (qualitative and quantitative)

- Log the actions -> Logging: I implemented BARE MINIMUM VERSION in prototype: JSON LOGGING

Prototype:

- Local

- Scenario 1 of 4 :

  - Should be participants’ own selection

  - 4 scenarios

  - Add chart

  - Initial decision without help of Agentic AI

  - Final decision with help of Agentic AI roles

  - Add title scenario 1: The confidential design disclosure

  - Dissent visible - 2 + 2

Study design:

- How do you know the selected 4 scenarios are relevant to participants - x10 relevant - common among eng discipline or discipline specific [AI generated highly ambiguous - details of prompts - Engineering] and SE only then evaluated by human shortlist 2 for the prototype.

  - 1st: profitable vs community

  - 2nd:

  - 3rd:

  - 4th:

- Own - without DV - with DV (choice by participant) - Final [limit to two scenarios] - 1st

- Own - without DV - with DV (based on 1st scenario selection) - Final [limit to two scenarios] 2nd

- 4 scenarios [Highly ambiguous only] ->

- With DV + Without DV

- Start with 2 without DV x 2

- 2 with DV x 2

  - Progressive disclosure, deliver feedback scenario by scenario

Sept 18th - presentation feedback

- RQ is asking in a leading way; make it more general (“Affect” instead of “improve” etc)

- How will AI responses be standardized to avoid the SAME agent giving different answers every time?

  - Ideas:

    - Guardrails (.MD)

    - Static (This is not as good because it is very similar to existing methods )

- Mockup - it is not immediately clear the user is getting AI advice; the (even psychologically and subconsciously) may alter user behaviour.

# 24 Sept 2026 | FIT4701/2 Meeting - Agenti…

## 24 Sept 2026 | FIT4701/2 Meeting - Agentic AI Platform

Attendees: ABM Russel Aryan Cyrus Ubaid Irfan

Notes

- Background

- Get started with Ethics and run before or during FYP-B.

  - Docs 80% Done, to be reviewed by Russel

- Access to overleaf

- Introduction - Background/Lit review - Methodology - Preliminary results - Future work in S2.

- RRQs

- Methodology - Calculation ??? source (why this eq should remain same in our project)

- Preliminary results - Personas, FR & NFRs, Mockups, survey design, data matched with RQs, identified all constraints, benchmarks (own + literature) - backed by stats…

- Week 9 - Introduction + Background/Lit review (including RQs) + WORK ON PROTOTYPE FIRST DRAFT DONE

- Week 10 - Methodology + Preliminary result

- Week 11- Final draft

- Week 12 - Submit

- Make Ai agents dynamic - Static [need to control the outcome + constraints/guardrails]:

- Need a working prototype for Ethics (req gathering + evaluation) FIRST DRAFT DONE

- Prototype is separate from survey questions (qualitative and quantitative)

- Log the actions -> Logging: I implemented BARE MINIMUM VERSION in prototype: JSON LOGGING

Sept 18th - presentation feedback

- RQ is asking in a leading way; make it more general (“Affect” instead of “improve” etc)

- How will AI responses be standardized to avoid the SAME agent giving different answers every time?

  - Ideas:

    - Guardrails (.MD)

    - Static (This is not as good because it is very similar to existing methods )

- Mockup - it is not immediately clear the user is getting AI advice; the (even psychologically and subconsciously) may alter user behaviour.

# 15 Sept 2026 | FIT4701/2 Meeting - Agentic AI Pla…

## 15 Sept 2026 | FIT4701/2 Meeting - Agentic AI Platform

Attendees: ABM Russel Aryan Cyrus Ubaid Irfan

Sept 18th - presentation feedback

- RQ is asking in a leading way; make it more general (“Affect” instead of “improve” etc)

- How will AI responses be standardized to avoid the SAME agent giving different answers every time?

  - Ideas:

    - Guardrails (.MD)

    - Static (This is not as good because it is very similar to existing methods )

- Mockup - it is not immediately clear the user is getting AI advice; the (even psychologically and subconsciously) may alter user behaviour.

# 8 Sept 2026 | FIT4701/2 Meeting

## 8 Sept 2026 | FIT4701/2 Meeting - Agentic AI Platform

Attendees: ABM Russel Aryan Cyrus

- Setup Git repository

- Select tech stack

Frontend: Vue+tailwind frontend (Typescript)

Backend: Express.js

Containerised using Docker

Firebase for any authentication, Database and deployment

Github for git management

Claude sonnet 5 for AI model

- Update the poster (exclude marketing items)

- Develop formula to calculate score

Honestly, maybe this is a bad idea. The scoring of agents DEPENDS ON SITUATION/Senario. Some scenarios TIME is most important, some scenarios LEGAL consideration is most important.

MY SOLUTION 1: Weighted scoring system CUSTOMISED for each scenario.

Example:

- Agent 1: 1 vote

- Agent 2: 2 votes

- Agent 3: 0.5 votes

etc

Weighting ranked by EXPERTS

WE DO NOT SHOW WEIGHTING TO USERS

- Draft ppt - 10 mins (Introduction + Background + Lit reviews + Aim + RQs + methodology + preliminary results (mockups, personas and demo of stack + week by week timeline till May 2027/ Gantt chart))

- Contact interview panel to confirm presentation time [URGENT 4pm Friday 18th]

- Populate slides

- Ethics application status? [Aryan: Filled some sections out, only document uploads to go]

- Overleaf access?

"Investigate whether adding governance mechanisms to a multi-agent AI ethics-training platform reduce students' over-reliance on the AI and improve their ethical decision-making”

Central RQ: Do we need governance mechanisms to a multi-agent AI ethics-training platform?

- Convert issues into RQs backed by lit survey

- Unique roles to each agent

- Poor decision making

- Should we use utilitarian approach to agree with agent’s decision

- How to validate the final decision?

- What are the different roles required in a multi-agent AI ethics-training platform?

- R Objective 1: Investigate the consequences of a multi-agent AI ethics-training platform

  - RQ1.1: Can we rely on a multi-agent AI ethics-training platform?

    - Measure: Trust metrics based on accuracy and/or reputation - CRAP approach - find similar for measuring AI agent reliability…

    - RQ1.1a: Can flexibility in choosing own agents or fixed set of agents  impact on ethical decision making?

      - Measure: System requirement - Fixed set of Agents vs Flexible Agents. Orchestration - sequentially  (rule-based pre-determined) or other - compare different architecture

      - Does restricting users from choosing their own AI agents influence their ethical reasoning, potentially causing users to converge toward similar decisions?

RQ1.2: Does incorporating governance mechanisms in a multi-agent AI ethics-training platform improve ethical decision making?

    - Measure: System requirement - with or without

    - 1.2a: Is the effect of [Gov mechanism] on over-reliance and accuracy stronger for contested/ambiguous ethical cases than for cases with high expert consensus Refer to RQ1.2a

      - Remember the study from last week? Where they tested ONLY ON LOW RISK DECISION? We can fill that gap!

    - 1.2b: Do governance mechanisms increase the quality of overall ethical decision? Refer to RQ1.2b

      - RQ1.2b.1: Define quality of ethical decision - Accuracy???

        - Measure: If accuracy then % of correct answers

      - [BUILDS ON ABOVE]: Does [chosen gov mechanism] improve the accuracy of students' final ethical decisions relative to expert-validated ground truth?

Measure: % of final decisions matching the expert-consensus answer

    - 1.2c: Do governance mechanisms increase the reliability (using utilitarian or similar) of overall ethical decision? Refer to RQ1.2c

      - RQ1.2c.1: Define reliability of ethical decision - based on consensus/consequences/risk?

        - Measure:

    - RQ1.2d: Does showing dissent among a pool of AI agents reduce students' over-reliance on incorrect AI advice, compared to a no-dissent-visibility condition? Measure: Behavioural over-reliance ratio discussed in prev meetings

    - 1.2e: Does [Gov mechanism] reduce students' self-reported trust in the AI's advice, and does that align with their behavioural over-reliance?

  - Does trust == reliance?

  - Measure: Jian Et Al has a scale: (PDF) Foundations for an Empirically Determined Scale of Trust in Automated Systems

Reliability = accuracy against expert validated ans.

Action:

- Draft the Week 8 slide deck - 10 mins   check the rubric.

- Inro+Related work -> gaps, RQs, Prelim work (design of the system Personas/FR/NFR/Mockups), Research design outline includes study design (quantitative/qualitative) using survey, Gantt chart/Week by week milestones plan for S2 delivery

- Overleaf template - IEEE format ()- Russel

- Initiate the MUHREC application??  Russel

In simple terms, explain the background and importance of this research - Do not include citations, explain all abbreviations and avoid using complex technical terms. - Refer to Readable's text scoring tool for tips to improve readability.

|  | List the aims or hypotheses of the research project |
| --- | --- |

|  | Give a brief overview of the research design |
| --- | --- |

NFR and FRS:

Some general ideas, it is very hard to know without know what the RQ actually is

FR:

Pre-:

- Selection of AI agents (Flexible choose your own agents from an existing agents skills vs pre-determined Fixed agents)

During:

- Multi-agent advice generation

  - distinct/specialised agent roles

- condition assignment

- ground-truth case bank

- incorrect-advice injection

- Agent consensus/disagreement control (whether/how agents disagree)

  - dissent surfacing/suppression (whether participant sees that disagreement)

Post-:

- decision capture; records initial/final decision AND reasoning

  - ethical/moral reasoning assessment (evaluates the recorded reasoning)

- revision/time logging

- Auto-scoring

- trust survey

- data export

- consent/withdrawal

- Scenario consensus/ambiguity classification (from RO4)

  - System needs some way to distinguish between:

    - High-consensus scenario (high expert consensus on ethically preferred decision)

    - ambiguous/contested scenario (potential disagreement about preferred decision)

NFR:

- Data integrity

- Latency

- privacy/anonymization

- Reliability

- Reproducibility

  - auditability/traceability: we need to reconstruct which scenario/condition/agent outputs led to each participant response.

- usability parity

- Security

- Maintainability

- Experimental consistency (ensuring experimental conditions differ only in intended manipulation)

- AI response consistency/controllability (our experiment needs control over AI outputs so the intended experimental condition actually occurs)

- Accessibility

Preliminary Mockup:

Flow: engineering ethics scenario → participant makes a decision → multi agent AI provides advice → participant can reconsider → final decision → collect measures

Ethics application : Design and Development of a multi-agent AI ethics-training platform.

Consider including in the background/lit survey/related work section.

- Over reliance definition -  IfMath behind the calculation - need to know variables….  recursion what is your goal - <10% considering constraints

- Over-reliance = (number of cases where the student's final decision matches the AI's incorrect advice) ÷ (total number of cases where the AI's advice was incorrect)

Action items

- Lit surveys: Create an excel spreadsheet

- Start the template for W12 initial paper - 4 pages - Russel

- Ethics approval MUHREC - Russel

- Work on objectives - add more )

  - Added 1.2, 2.1.1, 4.0 and 5.0

- Identify requirements (FR and NFR) for our multi-agent AI ethics-training platform. (fixed set of Agents or flexible options)

- Mockups + Personas

- Prepare for the Week 8 interview presentation (Context, background, Aim, RQs, RM overview, prelim findings, PoC.., plan for S2 research - Gantt chart)

- CRAP: find similar for measuring AI agent reliability…

- Draft answer for three Ethics application questions?

- Log into the following: https://ethicsapps.monash.edu/ActivityForm/Index

- Module - Risk, OH&S Frevvo, ?? Sarah -> Week 5 - Russel to recheck the list.

In simple terms, explain the background and importance of this research

Do not include citations, explain all abbreviations and avoid using complex technical terms.

Refer to Readable's text scoring tool for tips to improve readability.

List the aims or hypotheses of the research pro

Give a brief overview of the research design

- Students - 18+ (exclude Malaysia and Indonesia citizens)

- Junior Working professional 18+ (<2 years of experience) - What types of decision - Technical and tactical

- IF Senior Working professional 18+ (5+ years of experience) - What types of decision - Business and strategic

# 1 Sept 2026 | FIT4701/2 Meeting

## 1 Sept 2026 | FIT4701/2 Meeting - Agentic AI Platform

Attendees: ABM Russel Aryan Cyrus Ubaid Irfan

"Investigate whether adding governance mechanisms to a multi-agent AI ethics-training platform reduce students' over-reliance on the AI and improve their ethical decision-making”

Central RQ: [to refine] Do we need governance mechanisms to a multi-agent AI ethics-training platform?

- Convert issues into RQs backed by lit survey

- Unique roles to each agent

- Poor decision making

- Should we use utilitarian approach to agree with agent’s decision

- How to validate the final decision?

- What are the different roles required in a multi-agent AI ethics-training platform?

FR: Stages?? Pre-, during, post-

- R Objective 1: Investigate the consequences of a multi-agent AI ethics-training platform

  - RQ1.1: Can we rely on a multi-agent AI ethics-training platform?

    - Measure: Trust metrics based on accuracy and/or reputation - CRAP approach - find similar for measuring AI agent reliability…

    - RQ1.1a: Can flexibility in choosing own agents or fixed set of agents  impact on ethical decision making?

      - Measure: System requirement - Fixed set of Agents vs Flexible Agents. Orchestration - sequentially  (rule-based pre-determined) or other - compare different architecture

      - Does restricting users from choosing their own AI agents influence their ethical reasoning, potentially causing users to converge toward similar decisions?

RQ1.2: Does incorporating governance mechanisms in a multi-agent AI ethics-training platform improve ethical decision making?

    - Measure: System requirement - with or without

    - 1.2a: Is the effect of [Gov mechanism] on over-reliance and accuracy stronger for contested/ambiguous ethical cases than for cases with high expert consensus Refer to RQ1.2a

      - Remember the study from last week? Where they tested ONLY ON LOW RISK DECISION? We can fill that gap!

    - 1.2b: Do governance mechanisms increase the quality of overall ethical decision? Refer to RQ1.2b

      - RQ1.2b.1: Define quality of ethical decision - Accuracy???

        - Measure: If accuracy then % of correct answers

      - [BUILDS ON ABOVE]: Does [chosen gov mechanism] improve the accuracy of students' final ethical decisions relative to expert-validated ground truth?

Measure: % of final decisions matching the expert-consensus answer

    - 1.2c: Do governance mechanisms increase the reliability (using utilitarian or similar) of overall ethical decision? Refer to RQ1.2c

      - RQ3.1: Define reliability of ethical decision - based on consensus/consequences/risk?

        - Measure:

    - RQ1.2d: Does showing dissent among a pool of AI agents reduce students' over-reliance on incorrect AI advice, compared to a no-dissent-visibility condition? Measure: Behavioural over-reliance ratio discussed in prev meetings

    - 1.2e: Does [Gov mechanism] reduce students' self-reported trust in the AI's advice, and does that align with their behavioural over-reliance?

  - Does trust == reliance?

  - Measure: Jian Et Al has a scale: (PDF) Foundations for an Empirically Determined Scale of Trust in Automated Systems

Reliability = accuracy against expert validated ans.

Action:

- Draft the Week 8 slide deck - 10 mins  check the rubric.

- Inro+Related work -> gaps, RQs, Prelim work (design of the system Personas/FR/NFR/Mockups), Research design outline includes study design (quantitative/qualitative) using survey, Gantt chart/Week by week milestones plan for S2 delivery

- Overleaf template - IEEE format ()- Russel

- Initiate the MUHREC application??  Russel

In simple terms, explain the background and importance of this research - Do not include citations, explain all abbreviations and avoid using complex technical terms. - Refer to Readable's text scoring tool for tips to improve readability.

|  | List the aims or hypotheses of the research project |
| --- | --- |

|  | Give a brief overview of the research design |
| --- | --- |

NFR and FRS:

Some general ideas, it is very hard to know without know what the RQ actually is

FR:

Pre-:

- Selection of AI agents (Flexible choose your own agents from an existing agents skills vs pre-determined Fixed agents)

During:

- Multi-agent advice generation

  - distinct/specialised agent roles

- condition assignment

- ground-truth case bank

- incorrect-advice injection

- Agent consensus/disagreement control (whether/how agents disagree)

  - dissent surfacing/suppression (whether participant sees that disagreement)

Post-:

- decision capture; records initial/final decision AND reasoning

  - ethical/moral reasoning assessment (evaluates the recorded reasoning)

- revision/time logging

- Auto-scoring

- trust survey

- data export

- consent/withdrawal

- Scenario consensus/ambiguity classification (from RO4)

  - System needs some way to distinguish between:

    - High-consensus scenario (high expert consensus on ethically preferred decision)

    - ambiguous/contested scenario (potential disagreement about preferred decision)

NFR:

- Data integrity

- Latency

- privacy/anonymization

- Reliability

- Reproducibility

  - auditability/traceability: we need to reconstruct which scenario/condition/agent outputs led to each participant response.

- usability parity

- Security

- Maintainability

- Experimental consistency (ensuring experimental conditions differ only in intended manipulation)

- AI response consistency/controllability (our experiment needs control over AI outputs so the intended experimental condition actually occurs)

- Accessibility

Preliminary Mockup:

Flow: engineering ethics scenario → participant makes a decision → multi agent AI provides advice → participant can reconsider → final decision → collect measures

Ethics application : Design and Development of a multi-agent AI ethics-training platform.

Consider including in the background/lit survey/related work section.

- Over reliance definition -  IfMath behind the calculation - need to know variables….  recursion what is your goal - <10% considering constraints

- Over-reliance = (number of cases where the student's final decision matches the AI's incorrect advice) ÷ (total number of cases where the AI's advice was incorrect)

Action items

- Lit surveys: Create an excel spreadsheet

- Start the template for W12 initial paper - 4 pages - Russel

- Ethics approval MUHREC - Russel

- Work on objectives - add more )

  - Added 1.2, 2.1.1, 4.0 and 5.0

- Identify requirements (FR and NFR) for our multi-agent AI ethics-training platform. (fixed set of Agents or flexible options)

- Mockups + Personas

- Prepare for the Week 8 interview presentation (Context, background, Aim, RQs, RM overview, prelim findings, PoC.., plan for S2 research - Gantt chart)

- CRAP: find similar for measuring AI agent reliability…

- Draft answer for three Ethics application questions?

- Log into the following: https://ethicsapps.monash.edu/ActivityForm/Index

- Module - Risk, OH&S Frevvo, ?? Sarah -> Week 5 - Russel to recheck the list.

In simple terms, explain the background and importance of this research

Do not include citations, explain all abbreviations and avoid using complex technical terms.

Refer to Readable's text scoring tool for tips to improve readability.

List the aims or hypotheses of the research pro

Give a brief overview of the research design

- Students - 18+ (exclude Malaysia and Indonesia citizens)

- Junior Working professional 18+ (<2 years of experience) - What types of decision - Technical and tactical

- IF Senior Working professional 18+ (5+ years of experience) - What types of decision - Business and strategic

# 25 Aug 2026 | FIT4002 Seminar

## 25 Aug 2026 | FIT4002 Seminar

Attendees: Ubaid, Aryan, Russel

Notes

- Aim:

"Investigate whether adding governance mechanisms to a multi-agent AI ethics-training platform reduce students' over-reliance on the AI and improve their ethical decision-making”

Central RQ: [to refine] Do we need governance mechanisms to a multi-agent AI ethics-training platform?

- Convert issues into RQs backed by lot survey

- Unique roles to each agent

- Poor decision making

- Should we use utilitarian approach to agree with agent’s decision

- How to validate the final decision?

- What are the different roles required in a multi-agent AI ethics-training platform?

FR: Stages?? Pre-, during, post-

- R Objective 1: Investigate the consequences of a multi-agent AI ethics-training platform

  - RQ1.1: Can we rely on a multi-agent AI ethics-training platform?

    - Measure: Trust metrics based on accuracy and/or reputation - CRAP approach - find similar for measuring AI agent reliability…

RQ1.2: Does incorporating governance mechanisms in a multi-agent AI ethics-training platform improve ethical decision making?

    - Measure: System requirement - with or without

  - RQ1.3: Can flexibility in choosing own agents or fixed set of agents  impact on ethical decision making?

    - Measure: System requirement - Fixed set of Agents vs Flexible Agents. Orchestration - sequentially  (rule-based pre-determined) or other - compare different architecture

    - Does restricting users from choosing their own AI agents influence their ethical reasoning, potentially causing users to converge toward similar decisions?

  - RQ1.44: Does showing dissent among a pool of AI agents reduce students' over-reliance on incorrect AI advice, compared to a no-dissent-visibility condition? Measure: Behavioural over-reliance ratio discussed in prev meetings

- R Objective 2: Do governance mechanisms increase the quality of overall ethical decision? Refer to RQ1.2b

  - RQ2.1: Define quality of ethical decision - Accuracy???

    - Measure: If accuracy then % of correct answers

  - RQ2.1.1 [BUILDS ON ABOVE]: Does [chosen gov mechanism] improve the accuracy of students' final ethical decisions relative to expert-validated ground truth?

Measure: % of final decisions matching the expert-consensus answer

- R Objective 3: Do governance mechanisms increase the reliability (using utilitarian or similar) of overall ethical decision? Refer to RQ1.2c

  - RQ3.1: Define reliability of ethical decision - based on consensus/consequences/risk?

    - Measure:

- R Objective 4: Is the effect of [Gov mechanism] on over-reliance and accuracy stronger for contested/ambiguous ethical cases than for cases with high expert consensus Refer to RQ1.2a

  - Remember the study from last week? Where they tested ONLY ON LOW RISK DECISION? We can fill that gap!

- R Objective 5: Does [Gov mechanism] reduce students' self-reported trust in the AI's advice, and does that align with their behavioural over-reliance?

  - Does trust == reliance?

  - Measure: Jian Et Al has a scale: (PDF) Foundations for an Empirically Determined Scale of Trust in Automated Systems

Reliability = accuracy against expert validated ans.

NFR and FRS:

Some general ideas, it is very hard to know without know what the RQ actually is

FR:

Pre-:

- Selection of AI agents (Flexible choose your own agents from an existing agents skills vs pre-determined Fixed agents)

During:

- Multi-agent advice generation

  - distinct/specialised agent roles

- condition assignment

- ground-truth case bank

- incorrect-advice injection

- Agent consensus/disagreement control (whether/how agents disagree)

  - dissent surfacing/suppression (whether participant sees that disagreement)

Post-:

- decision capture; records initial/final decision AND reasoning

  - ethical/moral reasoning assessment (evaluates the recorded reasoning)

- revision/time logging

- Auto-scoring

- trust survey

- data export

- consent/withdrawal

- Scenario consensus/ambiguity classification (from RO4)

  - System needs some way to distinguish between:

    - High-consensus scenario (high expert consensus on ethically preferred decision)

    - ambigious/contested scenario (potential disagreement about preferred decision)

NFR:

- Data integrity

- Latency

- privacy/anonymization

- Reliability

- Reproducibility

  - auditability/traceability: we need to reconstruct which scenario/condition/agent outputs led to each participant response.

- usability parity

- Security

- Maintainability

- Experimental consistency (ensuring experimental conditions differ only in intended manipulation)

- AI response consistency/controllability (our experiment needs control over AI outputs so the intended experimental condition actually occurs)

- Accessibility

Preliminary Mockup:

Flow: engineering ethics scenario → participant makes a decision → multi agent AI provides advice → participant can reconsider → final decision → collect measures

Ethics application : Design and Development of a multi-agent AI ethics-training platform.

Consider including in the background/lit survey/related work section.

- Over reliance definition -  IfMath behind the calculation - need to know variables….  recursion what is your goal - <10% considering constraints

- Over-reliance = (number of cases where the student's final decision matches the AI's incorrect advice) ÷ (total number of cases where the AI's advice was incorrect)

Action items

- Lit surveys: Create an excel spreadsheet

- Start the template for W12 initial paper - 4 pages - Russel

- Ethics approval MUHREC - Russel

- Work on objectives - add more )

  - Added 1.2, 2.1.1, 4.0 and 5.0

- Identify requirements (FR and NFR) for our multi-agent AI ethics-training platform. (fixed set of Agents or flexible options)

- Mockups + Personas

- Prepare for the Week 8 interview presentation (Context, background, Aim, RQs, RM overview, prelim findings, PoC.., plan for S2 research - Gantt chart)

- CRAP: find similar for measuring AI agent reliability…

- Draft answer for three Ethics application questions?

- Log into the following: https://ethicsapps.monash.edu/ActivityForm/Index

- Module - Risk, OH&S Frevvo, ?? Sarah -> Week 5 - Russel to recheck the list.

In simple terms, explain the background and importance of this research

Do not include citations, explain all abbreviations and avoid using complex technical terms.

Refer to Readable's text scoring tool for tips to improve readability.

List the aims or hypotheses of the research pro

Give a brief overview of the research design

- Students - 18+ (exclude Malaysia and Indonesia citizens)

- Junior Working professional 18+ (<2 years of experience) - What types of decision - Technical and tactical

- IF Senior Working professional 18+ (5+ years of experience) - What types of decision - Business and strategic

# 18 Aug 2026 | FIT4701/2 Meeting - Agentic AI Plat…

## 18 Aug 2026 | FIT4701/2 Meeting - Agentic AI Platform

Attendees: ABM Russel Aryan Cyrus Ubaid Irfan

Apology: Ubaid

Notes

- 1st paper: Cognitive forcing function to reduce over reliance.

  - Three forcing functions (N=199)

- 2nd paper: Results were incorrect due to over reliance

  - When they went wrong

- Over reliance definition

- Measurement

  - Metrics what to measure

  - Opinion survey open to all

- Governance system x 3

- Go ahead with Narrative lit review (not systematic lit reviews)

- COSMIN type framework to evaluate - find alternatives for our project

COSMIN Taxonomy of Measurement Properties • COSMIN

- Six thinking hats as roles ?

- https://www.debonogroup.com/services/core-programs/six-thinking-hats/

- Aim:

"Investigate whether adding governance mechanisms to a multi-agent AI ethics-training platform reduce students' over-reliance on the AI and improve their ethical decision-making”

Central RQ: [to refine] Do we need governance mechanisms to a multi-agent AI ethics-training platform?

- Issues:

  - Unique roles to each agent

  - Poor decision making

  - Should we use utilitarian approach to agree with agent’s decision

  - How to validate the final decision?

  - What are the different roles required in a multi-agent AI ethics-training platform?

- R Objective 1: Investigate the consequences of a multi-agent AI ethics-training platform

- R Objective 2: How could we incorporate governance mechanisms in a multi-agent AI ethics-training platform?

- R Objective 3: Do governance mechanisms increase the quality of overall ethical decision?

- R Objective 5: Do governance mechanisms increase the reliability (using utilitarian or similar) of overall ethical decision?

- Any other objectives…

Sub RQs will be based on these objectives

Action items

- Lit surveys: Create an excel spreadsheet

- Start the template for W12 initial paper - 4 pages - Russel

- Ethics approval MUHREC - Russel

- Work on objectives - add more

- Excel summarise the studies (Abstract, method, findings , limitations etc)

# 04 Aug 2026 | FIT4701/2 Meeting - Agentic AI Plat…

## 4 Aug 2026 | FIT4701/2 Meeting - Agentic AI Platform

Attendees: ABM Russel Aryan Cyrus Ubaid Irfan

Requirements could be from lit OR surveys

Learning or self l

Meeting Notes:

https://onlineethics.virginia.edu/taxonomy/term/826

Russel ABM Russel  to  Everyone 6:57 PM

Agent4EDU

EduMAS

- Week 3 – Milestone 1: Launch (Moodle quiz)

- Week 5 – OH&S Risk Assessment (competency hurdle)

  - For the Clayton cohort, completing the online OHS and risk assessment training modules and associated tasks is mandatory for all students, including those undertaking computer‑based projects. Depending on the project type, students may also require further lab/building inductions and submission of RA on SARAH.

- Week 8 – Milestone 2: Confirmation (competency hurdle)

- Week 12 – Milestone 3: Initial Paper (competency hurdle)